## Лист1
| Dima | Roman | Stas |  |  |  | Roman's hours | Dima's hours | Stas's hours
BE meeting (W1) | 1 | 1 | 1 |  |  | Capacity | 104 | 96 | 104
BE meeting(W2) | 1 | 1 | 1 |  |  | Planned work | 104 | 96 | 104
BE meeting(W3) | 1 | 1 | 1 |  |  | Extra | 0 | 0 | 0
Code health meeting (W1) | 1 | 1
Code health meeting(W2) | 1 | 1
Code health meeting(W3) | 1 | 1
Retro | 2 | 2 | 2
Grooming | 2 | 2 | 2
Daily | 5 | 5 | 5
130039:Create 4 new multi-codes to conduct Imaging exam
Check multicodes in BD for all ENVs (Beta, Prod1, Prod3, AU) |  | 2
Add new multicodes to config |  | 1 | 3 | multiCodeProcedureService(MultiCodeProcedureService, ['2BW2PA', '4BW2PA', '4BW4PA', '2BW2OCC'] | DONE
Insert multicodes into GlobalMultiCodeProcedure table |  | 1 | 3 | GlobalMulticodeProcedure_CL_Insert11_311.xml | DONE
Insert multicodes into GlobalMultiCodeProcedureRule table |  | 1 | 4 | GlobalMultiCodeProcedureRule_CL_Insert13_311.xml | DONE
Update existing multicodes OrganizationProcedure |  |  | 1 | OrganizationProcedure_CL_Update64_311.xml | DONE
Insert multicodes to Organization Procedure table (Multicode should not be empty) |  | 1 | 5 | OrganizationProcedure_CL_Insert65_311.xml | DONE
Insert multicodes into PracticeProcedureAU |  | 1 | 1 | PracticeProcedureAU_CL_Insert15_311.xml | DONE
Insert multicodes into RCI DB |  | 1 | 2 | ProcedureCode_CL_Insert10.xml | DONE
Insert multicodes into MultiCodeProcedureRule |  | 1 | 3 | MultiCodeProcedureRule_CL_Insert13_311.xml | DONE
Dev testing AU and US/Athena |  | 3 | 4
Code review |  | 2 | 4
Local testing |  | 4
Bug fixing |  |  | 8
105237:Pagination on Unsigned Clinical notes
Combine GORM methods in ClinicalNoteService.findUnsignedForToday | 10
Combine GORM methods in ClinicalNoteService.findUnsignedForPast | 6
Add pagination logic and ordering logic | 8
Add limits | 4
Dev testing | 6
Unit tests | 6 |  | 24
Local testing | 6
Code review | 10
Bug fixing | 8
BIP | 17
Eligibility | 0 | 66
Packaging??? |  | 5 | 30